## Final_Renaissance_Burndown
|  |  |  | SPRINT 1 | [6 empty] | SPRINT 2 | [6 empty] | SPRINT 3 | [6 empty] | SPRINT 4
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 10 x 6) | D1 | D2 | D3 | D4 | D8 | D9 | D10 | D11 | D15 | D16 | D17 | D18 | D22 | D23 | D24 | D25 | D22 | D23 | D24 | D25 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-26 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-05 | 2021-04-07 | 2021-04-09 | 2021-04-11 | 2021-04-12 | 2021-04-14 | 2021-04-16 | 2021-04-17 | 2021-04-22 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-30 | 2021-05-03 | 2021-05-04 | 2021-05-06 | 2021-05-07 | 2021-05-10 | 2021-05-11 | 2021-05-13
|  |  |  | 161 | 155 | 149 | 143 | 137 | 131 | 125 | 119 | 113 | 107 | 101 | 95 | 89 | 83 | 77 | 71 | 65 | 59 | 53 | 47 | 41 | 35 | 29 | 23 | 17 | 11 | 4 | 0 | Ideal Burndown
|  |  | 161 | 162 | 157 | 154 | 152 | 152 | 148 | 145 | 142 | 138 | 135 | 130 | 129 | 118 | 109 | 103 | 98 | 93 | 85 | 74 | 66 | 59 | 55 | 45 | 38 | 31 | 17 | 12 | 0 | Remaining Hrs (Total)
Login in / Register (UI+Backend), View and Search transactions | Understand requirements, identify classes and familiarize with MERN stack | Surabhi | 4 | 2021-03-15: 4; 2021-03-16: 3; 2021-03-17: 3; 2021-03-18: 2; 2021-03-26: 2; 2021-03-31: 1; 2021-04-01: 0
| Design Business Logic and backend for user Login | Surabhi | 5 | 2021-03-15: 5; 2021-03-16: 5; 2021-03-17: 5; 2021-03-18: 5; 2021-03-26: 5; 2021-03-31: 5; 2021-04-01: 5; 2021-04-02: 5; 2021-04-05: 4; 2021-04-07: 4; 2021-04-09: 2; 2021-04-11: 1; 2021-04-12: 1; 2021-04-14: 0
| Implement Front-End Code for user login | Surabhi | 4 | 2021-03-15: 4; 2021-03-16: 4; 2021-03-17: 4; 2021-03-18: 4; 2021-03-26: 4; 2021-03-31: 4; 2021-04-01: 4; 2021-04-02: 4; 2021-04-05: 4; 2021-04-07: 3; 2021-04-09: 3; 2021-04-11: 3; 2021-04-12: 2; 2021-04-14: 1; 2021-04-16: 0
| Implement Back-End Code for admin login | Surabhi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 0
| Implement Front-End Code for admin login | Surabhi | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
| Implement UI + Backend for user profile page | Surabhi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 0
| Implement UI + Backend for admin home page | Surabhi | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 4 | 4 | 4 | 2 | 0
| Implement backend + frontend for view bill pay transactions | Surabhi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 1 | 0
| Implement backend + frontend search transactions | Surabhi | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0
| Write Documentation - Burndown chart update/Scrum updates/other diagrams | Surabhi | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create new account, delete account(API), fetchAccountBalance(API), fetchBalanceFromUserName (UI + API) | Understand requirements, identify classes and familiarize with MERN stack | Arpitha | 4 | 2021-03-15: 4; 2021-03-16: 4; 2021-03-17: 3; 2021-03-18: 3; 2021-03-26: 3; 2021-03-31: 2; 2021-04-01: 2; 2021-04-02: 0
| Design Business Logic and backend for createAccount | Arpitha | 8 | 2021-03-15: 8; 2021-03-16: 8; 2021-03-17: 8; 2021-03-18: 8; 2021-03-26: 8; 2021-03-31: 8; 2021-04-01: 8; 2021-04-02: 8; 2021-04-05: 6; 2021-04-07: 6; 2021-04-09: 5; 2021-04-11: 5; 2021-04-12: 2; 2021-04-14: 2; 2021-04-16: 2; 2021-04-17: 0
| Implement front end for createAccount | Arpitha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 0
| Design Business Logic and backend for deleteAccount | Arpitha | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Business Logic and backend for fetchAccountBalance | Arpitha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Business Logic, backend and front end for fetchBalanceFromUserName | Arpitha | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | 0
| Write Documentation - Burndown chart update/Scrum updates/other diagrams | Arpitha | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Transfer funds, View Transactions, Deployment Transfer funds api + Update balance apis, Fetch transactions api, UI: transfer, view transactions, Deployment | Understand requirements, identify classes and familiarize with MERN stack | Gayathri | 4 | 2021-03-15: 4; 2021-03-16: 3; 2021-03-17: 3; 2021-03-18: 2; 2021-03-26: 2; 2021-03-31: 1; 2021-04-01: 1; 2021-04-02: 0
| Design Business Logic and backend for transfer funds | Gayathri | 8 | 2021-03-15: 8; 2021-03-16: 8; 2021-03-17: 8; 2021-03-18: 8; 2021-03-26: 8; 2021-03-31: 8; 2021-04-01: 8; 2021-04-02: 8; 2021-04-05: 7; 2021-04-07: 7; 2021-04-09: 5; 2021-04-11: 5; 2021-04-12: 3; 2021-04-14: 0
| Design Business Logic and backend for update balance | Gayathri | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 3 | 2 | 0
| Implement front end for transfer between accounts | Gayathri | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 3 | 3 | 2 | 0
| Implement front end for view transactions | Gayathri | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0
| Deployment on AWS | Gayathri | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 0
| Write Documentation - Burndown chart update/Scrum updates/other diagrams | Gayathri | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
1.One time bill payments for external payees. 2.Closing existing accounts(UI). 3.Add transactions such as manual refunds | Understand requirements, identify classes and familiarize with MERN stack | Priti | 4 | 2021-03-15: 4; 2021-03-16: 4; 2021-03-17: 3; 2021-03-18: 3; 2021-03-26: 3; 2021-03-31: 2; 2021-04-01: 0
| Design Business Logic and backend for bill pay component | Priti | 8 | 2021-03-15: 8; 2021-03-16: 8; 2021-03-17: 8; 2021-03-18: 8; 2021-03-26: 8; 2021-03-31: 8; 2021-04-01: 8; 2021-04-02: 8; 2021-04-05: 8; 2021-04-07: 6; 2021-04-09: 6; 2021-04-11: 6; 2021-04-12: 3; 2021-04-14: 2; 2021-04-16: 0
| Implement Front-End Code for bill pay | Priti | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 3 | 3 | 2 | 1 | 0
| Design Business Logic and backend for Admin manual refunds | Priti | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 3 | 2 | 0
| Implement Front-End Code for Admin manual refunds | Priti | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 1 | 1 | 0
| Design Front end for delete Account | Priti | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Implement UI + Backend for one time and recurring wrt bill pay | Priti | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
| Write Documentation - Burndown chart update/Scrum updates/other diagrams | Priti | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
TEAM | Ideal | Breakdown
Surabhi Govil | 40 hours | 45
Gayathri Pulagam | 40 hours | 42
Priti Sharma | 40 hours | 38
Arpitha Gurumurthy | 40 hours | 36
Total Available Hours During Sprint: | 160 hours for the project | 161 hours in total

## Burndown
Series 1 | Ideal breakdown
Series 2 | Team breakdown